## Dashboard
RCA MVP — Progress Tracker
Updated 2026-06-09 - Verified from code - Track A 20/57 done - Track B 8/8 done · EPIC-005 tier catalogs deferred (Phase 1: all tools exposed)
Overall
Bucket | Total | Done | In progress | Blocked | Not started
Track A (Product)
Track B (Simulators)
Gaps
Epics — Track A
Epic | Total | Done | In progress | Blocked | Status
EPIC-001 Foundations
EPIC-012 MAR
EPIC-003 TRS
EPIC-004 Templates
EPIC-013 Connectors
EPIC-005 MCP
EPIC-006 Temporal
EPIC-007 Agents
EPIC-008 HITL UI
EPIC-009 Eval
EPIC-010 Observability
EPIC-011 Pilot
Epics — Track B
Epic | Total | Done | In progress | Blocked | Status
EPIC-002 Simulators
This Week
Week | Track A focus |  | Track B focus
W1 (Jun 8-12) | S1.1 monorepo, S1.2 contracts, S1.3 docker-compose |  | S2.1 fixture + S2.8 realism (Days 1-2), then S2.7 MQTT (Days 3-4)

## Burn-up
12-Week Burn-up Plan
Week | Track A plan | Track B plan | Planned stories | Actual done | Notes
W1 (Jun 8-12) | Contracts, monorepo, docker-compose, Alembic | Fixture loader, MQTT sim, OPC UA sim | 8
W2 (Jun 15-19) | MAR schemas + resolve + get + search | SharePoint/S3 sim | 8
W3 (Jun 22-26) | TRS schemas + resolve_tag, Templates loader | PI sim | 8
W4 (Jun 29-Jul 3) | connector_sdk, MCP tier registration | Maximo sim, SAP sim | 8
W5 (Jul 6-10) | PI connector vs PI sim, MCP catalog | Realism harness | 6
W6 (Jul 13-17) | Maximo connector vs Maximo sim | (complete) | 4
W7 (Jul 20-24) | SAP/Document connectors, Temporal probe | — | 6
W8 (Jul 27-31) | Tier 1-2 agents (Scope, Evidence) | — | 4
W9 (Aug 3-7) | Tier 3-4 agents (Reason, Govern) + HITL UI | — | 5
W10 (Aug 10-14) | Eval harness + golden set | — | 4
W11 (Aug 17-21) | Observability, cost dashboard | — | 3
W12 (Aug 24-28) | Pilot: parity tests, customer configs, runbook | — | 4

## Track A
ID | Story | Tracker (Jun-4) | Verified (Jun-9) | Diff | Dep | Notes | Docs
S1.1 | Monorepo setup (packages/, infra/, scripts/, tests/) | Not started | Done | up ahead | — |  | docs/foundations/EPIC-001-foundations.md
S1.2 | Pydantic v2 contracts (closes G1: AssetDescriptor, TagDescriptor, ProbeTrigger, etc.) | Not started | Done | up ahead | — | SPEC-001 + SPEC-012 | docs/foundations/SPEC-001-evidence-bundle.md + SPEC-012
S1.3 | docker-compose dev stack (Postgres, Neo4j, Temporal, MinIO) | Not started | Done | up ahead | — |  | docs/foundations/WEEK-1-QUICKSTART.md
S1.4 | Alembic migrations baseline | Not started | Done | up ahead | S1.3 |  | docs/foundations/EPIC-001-foundations.md
S1.5 | Round-trip contract test | Not started | Done | up ahead | S1.2 |  | docs/foundations/SPEC-001-evidence-bundle.md
S12.1 | MAR schemas + Postgres tables | Not started | Done | up ahead | S1.2, S1.4 |  | docs/mar/SPEC-011-master-asset-registry.md
S12.2 | MAR.resolve(name/site) → asset_id | Not started | Done | up ahead | S12.1 |  | docs/mar/SPEC-011-master-asset-registry.md
S12.3 | MAR.get(asset_id) → AssetDescriptor | Not started | Done | up ahead | S12.1 |  | docs/mar/SPEC-011-master-asset-registry.md
S12.4 | MAR.search + hierarchy traversal | Not started | Done | up ahead | S12.1 |  | docs/mar/SPEC-011-master-asset-registry.md
S12.5 | MAR ↔ PI AF source adapter | Not started | Not started | = | S13.2 | Sim-backed first | docs/mar/EPIC-012-master-asset-registry.md
S12.6 | MAR ↔ Maximo source adapter | Not started | Not started | = | S13.3 | Sim-backed first | docs/mar/EPIC-012-master-asset-registry.md
S12.7 | MAR ↔ Spreadsheet bootstrap | Not started | Not started | = | S13.6 |  | docs/mar/EPIC-012-master-asset-registry.md
S12.8 | MAR ↔ SAP PM adapter | Not started | Not started | = | S13.4 | Sim-backed first | docs/mar/EPIC-012-master-asset-registry.md
S3.1 | TRS schemas + Postgres tables | Not started | Done | up ahead | S1.2, S1.4 |  | docs/trs/SPEC-003-tag-resolution-service.md
S3.2 | TRS.resolve_tag(tag) → tag_id + meta | Not started | Done | up ahead | S3.1 |  | docs/trs/SPEC-003-tag-resolution-service.md
S3.3 | TRS.search + TRS.get | Not started | Done | up ahead | S3.1 |  | docs/trs/SPEC-003-tag-resolution-service.md
S3.4 | UNS BIRTH/DEATH consumer → TRS upserts | Not started | Not started | = | S3.1, S13.7 |  | docs/trs/EPIC-003-trs.md
S3.5 | PI AF tag enumeration → TRS | Not started | Not started | = | S13.2 | Sim-backed first | docs/trs/EPIC-003-trs.md
S3.6 | Unresolved-tag queue + HITL hook | Not started | Not started | = | S3.2 |  | docs/trs/EPIC-003-trs.md
S4.1 | Template loader + validator | Not started | Not started | = | S1.2 | SPEC-015 | docs/templates/SPEC-015-equipment-template-schema.md
S4.2 | Centrifugal pump template v0.3.1 | Not started | Not started | = | S4.1 | From rca_pump_ref_bundle | docs/templates/SPEC-015-equipment-template-schema.md
S4.3 | MCP tools: template.get / list / validate | Not started | Not started | = | S4.1, S5.1 |  | docs/templates/EPIC-004-templates.md
S4.4 | Overlay enforcement (customer overrides base) | Not started | Not started | = | S4.1 |  | docs/templates/SPEC-010-overlay-learning.md
S13.1 | connector_sdk: BaseConnector ABC + lifecycle (UNBLOCKS ALL OTHERS) | Not started | Done | up ahead | S1.2 | ADR-0012 | docs/connectors/EPIC-013-connectors.md + SPEC-002
S13.2 | PI connector (Web API + AF) | Not started | Done | up ahead | S13.1, S2.2 |  | docs/connectors/EPIC-013-connectors.md
S13.3 | Maximo connector (REST) | Not started | Done | up ahead | S13.1, S2.3 |  | docs/connectors/EPIC-013-connectors.md
S13.4 | SAP PM connector (OData) | Not started | Done | up ahead | S13.1, S2.4 |  | docs/connectors/EPIC-013-connectors.md
S13.5 | OPC UA connector | Not started | Done | up ahead | S13.1, S2.5 |  | docs/connectors/EPIC-013-connectors.md
S13.6 | Document connector (SharePoint/S3) | Not started | Done | up ahead | S13.1, S2.6 |  | docs/connectors/EPIC-013-connectors.md
S13.7 | MQTT/UNS connector | Not started | Done | up ahead | S13.1, S2.7 |  | docs/connectors/EPIC-013-connectors.md
S13.8 | Contract tests: connector ↔ simulator parity | Not started | Done | up ahead | S13.2-S13.7 |  | docs/connectors/EPIC-013-connectors.md
S13.9 | Credential broker integration | Not started | In progress | up ahead | S13.1 |  | docs/connectors/SPEC-002-mcp-tool-contracts.md
S5.1 | MCP tier registration + auth | Not started | Not started | Deferred | — |  | docs/mcp/EPIC-005-mcp-servers.md
S5.2 | MCP catalog per tier (Tier 1-4) | Not started | Not started | Deferred | — |  | docs/mcp/EPIC-005-mcp-servers.md
S5.3 | Rate limit + budget guard | Not started | Not started | Deferred | — |  | docs/mcp/EPIC-005-mcp-servers.md
S6.1 | Probe workflow skeleton | Not started | Not started | = | S1.2 |  | docs/temporal/SPEC-004-probe-workflow.md
S6.2 | Probe trigger ingestion + dedup | Not started | Not started | = | S6.1 | SPEC-012 | docs/temporal/SPEC-012-probe-trigger-schema.md
S6.3 | HITL signals (approve/reject/escalate) | Not started | Not started | = | S6.1 |  | docs/hitl/SPEC-005-hitl-gates.md
S6.4 | Tenant onboarding workflow | Not started | Not started | = | S6.1 | SPEC-013 | docs/foundations/SPEC-013-tenant-onboarding.md
S6.5 | Retry/timeout/SLA policies | Not started | Not started | = | S6.1 |  | docs/temporal/SPEC-004-probe-workflow.md
S7.1 | Tier 1 Scope agent (LangGraph) | Not started | Not started | = | S5.2 |  | docs/agents/SPEC-006-agent-tier-graphs.md
S7.2 | Tier 2 Evidence agent | Not started | Not started | = | S5.2 |  | docs/agents/SPEC-006-agent-tier-graphs.md
S7.3 | Tier 3 Reason agent | Not started | Not started | = | S7.2 |  | docs/agents/SPEC-006-agent-tier-graphs.md
S7.4 | Tier 4 Govern agent | Not started | Not started | = | S7.3, S6.3 |  | docs/agents/SPEC-006-agent-tier-graphs.md
S8.1 | Review screen (probe + evidence) | Not started | Not started | = | S6.3 |  | docs/hitl/EPIC-008-hitl-ui.md
S8.2 | Approve/reject + signal routing | Not started | Not started | = | S8.1, S6.3 |  | docs/hitl/SPEC-005-hitl-gates.md
S8.3 | Onboarding gates UI | Not started | Not started | = | S6.4 |  | docs/foundations/SPEC-013-tenant-onboarding.md
S9.1 | Replay runner (probe.jsonl) | Not started | Not started | = | S6.1 |  | docs/eval/EPIC-009-evaluation-harness.md
S9.2 | Scoring harness | Not started | Not started | = | S9.1 |  | docs/eval/EPIC-009-evaluation-harness.md
S9.3 | 10-probe golden set | Not started | Not started | = | S9.1 |  | docs/eval/EPIC-009-evaluation-harness.md
S10.1 | OpenTelemetry instrumentation | Not started | Not started | = | — |  | docs/observability/EPIC-010-observability.md
S10.2 | Cost dashboard (per-tenant, per-tier) | Not started | Not started | = | S10.1 |  | docs/observability/EPIC-010-observability.md
S10.3 | HITL dashboard (queue + SLA) | Not started | Not started | = | S10.1 |  | docs/observability/EPIC-010-observability.md
S11.1 | Parity tests: sim vs real connector | Not started | Not started | = | S13.8 |  | docs/pilot/EPIC-011-pilot-readiness.md
S11.2 | Customer configs (overlays + creds) | Not started | Not started | = | S4.4, S13.9 |  | docs/pilot/EPIC-011-pilot-readiness.md
S11.3 | Runbook + incident playbooks | Not started | Not started | = | — |  | docs/pilot/EPIC-011-pilot-readiness.md
S11.4 | Pilot acceptance gate | Not started | Not started | = | S11.1-S11.3 |  | docs/pilot/EPIC-011-pilot-readiness.md

## Track B
Order | ID | Story | Tracker (Jun-4) | Verified (Jun-9) | Diff | Dep | Docs | Notes
1 | S2.1 | Fixture loader + manifest schema ⚑ FOUNDATION — start here | Not started | Done | up ahead | S1.2 | docs/simulators/SPEC-014-simulator-fixture-schema.md | Blocks S2.2-S2.7. Day 1-2.
2 | S2.8 | Realism harness (drift, jitter, fault injection) ⚑ FOUNDATION | Not started | Done | up ahead | S2.1 | docs/simulators/SPEC-007-simulator-behavior.md | Day 1-2, parallel with S2.1.
3 | S2.7 | MQTT/UNS simulator (Mosquitto + Sparkplug B publisher) | Not started | Done | up ahead | S2.1 | docs/simulators/EPIC-002-simulators.md §S2.7 | Day 3-4. Simplest — just publish bytes. Validates fixture loader end-to-end.
4 | S2.5 | OPC UA simulator (asyncua server + nodes) | Not started | Done | up ahead | S2.1 | docs/simulators/EPIC-002-simulators.md §S2.5 | Day 5-7. Well-documented protocol.
5 | S2.6 | SharePoint / S3 document simulator (FastAPI + MinIO) | Not started | Done | up ahead | S2.1 | docs/simulators/EPIC-002-simulators.md §S2.6 | Week 2. Documents for evidence.
6 | S2.2 | PI Historian simulator (PI Web API REST subset) | Not started | Done | up ahead | S2.1 | docs/simulators/EPIC-002-simulators.md §S2.2 | Week 3. Most surface area; biggest payback.
7 | S2.3 | Maximo simulator (OSLC REST: work orders, assets, locations) | Not started | Done | up ahead | S2.1 | docs/simulators/EPIC-002-simulators.md §S2.3 | Week 4. CMMS data.
8 | S2.4 | SAP PM simulator (OData v2: equipment, notifications) | Not started | Done | up ahead | S2.1 | docs/simulators/EPIC-002-simulators.md §S2.4 | Week 4, parallel with Maximo.

## Blockers
Active Blockers
Add rows as blockers are discovered. Status auto-colors.
Opened | Story | Description | Owner | Status | Resolution

## Decisions
Decision Log
Architecture and process decisions. Promote significant ones to ADRs in docs/adrs/.
Date | Decision | Context / Rationale | Outcome
2026-06-04 | Connectors own the MCP contract; simulators stand in for sources | Original framing put simulators as 'fake connectors,' which made connector + simulator look like one workstream. Reframed to clarify: connectors are the integration layer; simulators implement the same source-side interface as real systems. | Promoted to ADR-0012; unblocks parallel Track B work
2026-06-09 | Skip tier-bounded tool catalogs for Phase 1 MVP; expose all MCP tools | With only ~5-10 tools total, per-tier catalog filtering (EPIC-005 S5.1/S5.2) solves problems that don't bite at this scale: context bloat and least-privilege isolation only pay off at large tool counts. Phase 1 agents receive the full toolset from the connected MCP servers directly. | EPIC-005 tier work deferred to post-Phase-1. Revisit when tool count grows or Govern-tier write-backs need guarding. ADR-0005 / SPEC-002 tier-catalog language now aspirational, not Phase-1.

## Gaps
Gap Tracker
Must-fix gaps identified pre-kickoff. G2-G6 closed by SPEC-001/012/013/014/015.
Gap | Description | Status | Closed by | Owner / Notes
G1 | Pydantic v2 contracts not yet implemented | In progress | S1.2 (spec ready) | Code authored in Claude Code
G2 | AssetDescriptor / TagDescriptor not formally specified | Done | SPEC-001 patch | Closed pre-kickoff
G3 | Probe trigger schema undefined | Done | SPEC-012 | Closed pre-kickoff
G4 | Tenant onboarding workflow undefined | Done | SPEC-013 | Closed pre-kickoff
G5 | Simulator fixture schema undefined | Done | SPEC-014 | Closed pre-kickoff
G6 | Equipment template schema undefined | Done | SPEC-015 | Closed pre-kickoff
G7 | Auth & credential broker spec | Not started | Deferred | Post-W4
G8 | Knowledge graph schema (Neo4j) | Not started | Deferred | Tier 3 work
G9 | Probe state machine formalization | Not started | Deferred | Folded into S6.1
G10 | Budget enforcement spec | Not started | Deferred | S5.3 covers basics
G11 | Eval scoring rubric | Not started | Deferred | S9.2 will define
G12 | Multi-tenant isolation guarantees | Not started | Deferred | Post-MVP

## Lessons
Lessons Learned
Capture insights as they emerge — what worked, what didn't, what to change.
Date | Topic | Lesson | Action / Follow-up
2026-06-04 | Simulators | Sim vibration is trend-only (scalar RMS trends, no FFT spectra). Acceptable for MVP — agent reasons on thresholds/trends from the template. | Pilot validation against real PI data must cover spectrum cases (1x/2x/broadband signatures).